## Sheet1
Sr. No. | Feature | Requirement Details | Applies to | Included in Rel 4 | Status | Dependency | Dependency | Remarks | T Shirt Sizing
Due Date
1 | ACL (Access Control List) Permissions (Roles) | This feature will allow users to grant permissions based on project KPIs such as service tickets, assets to access them on customer portal. | All OpCos | Yes | QA- In Progress | None |  | Ready for Demo | L
Admins can manage their users' permissions for viewing right set of information on the MyRicoh portal for dashboard KPIs present on it.
2 | Closed Order Enhancements | Include another field in Open Order Table Grid: Tracking URL to capture the Track & Trace URL received from Snowflake against an order | RAP, RPH | Yes | QA- In Progress | Order API updates to capture Track & trace URL info | 2025-01-14 | Ready for Demo with dummy data | S
Also, manage status filter for RAP only to allow users to refine orders based on values present in Status Filter
3 | Toner Order Enhancements | Display Toner level while ordering a consumable request | All OpCos | Yes | On Hold | Need API for getting updated on toner information | 2025-01-14 | On Hold till 10th Jan for dependencies | L
|  | Consider volume consideration of toner levels while showing the values in % for better user experience and plan their print runs in advance. |  |  |  | 1. % volume
|  | Also, allow user to select qty for production devices and select multi colors for colored devices only |  |  |  | 2. Device Size: Production or non-production
3. Device Type: Colored or Mono
4 | Self Registration | This feature allow Ricoh to onbaord all of their customers and their accounts automatically by making their data exposed to Snowflake APIs. | RNZ, RPH | Yes | On Hold | Customer Snowflake API updates for RNZ, RPH and RSP | 2025-01-16 |  | S
This feature will also allow existing customers to update their account information if any new sub-account needs to be added/modified
5 | Catalog Creation | This feature will allow Ricoh to provide product information via Snowflake for their customers to view on MyRicoh portal. | All OpCos | Yes | On Hold | Catalog Snowflake API - Single API for Public and Custom catalog both | 2025-01-16 |  | L
It will enable Ricoh and customer to view the information without waiting much for importing the data manually in Spryker for them to view on the portal.
6 | Catalog mapping automation -Public or Customer specific catalog | This feature will enable Ricoh product teams to show products based on catalog type. As a customer, they could either have customer-sepcific catalog OR public catalog for purchasing on the portal. This will help Ricoh and customers to view the mutually agreed products for procurement and make things faster in terms of aquisition of new assets | All OpCos | Yes | On Hold | Public or custom Catalog mapping - Need updated flags in Customer Initial and Incremental Load APIs | 2025-01-16 |  | XL
7 | Customer Live Inquiry | Customer who login to the customer portal can directly ask question and inquiry to the Call Center Agent using Microsoft D365 Customer Service Workspace. | All OpCos | Yes | TBD | Need update on implementation approach considering data limitation to move out of regions |  |  | TBD
8 | Reporting | Various reports can be generated for the data that is being displayed on the portal for company Admins as well as for Ricoh internal users for further investigations and actions needed on them. | RNZ, RPH | Yes | On Hold | Desired reports per customer needs to be added in Snowflake API for visisbilty to customer when menu is accessed | 2025-01-16 |  | S
This can be achieved by exposing Power BI reports to Customer portal using APIs
9 | Relocation Enhancement- | This feature will allow customers to cancel the submitted requests so that new request can be created when something is not appropriate on submitted request OR by mistake the request was created by the customer. | All OpCos | Yes | To be started | None |  |  | L
| Cancellation ​Workflow | This feature will also allow Ricoh team to release the assets which are locked for more the defined period by the customer
10 | Relocation Enhancement- | This feature will allow Ricoh internal teams to add comments for OFT team and externally to customers for better communication. | All OpCos | Yes | To be started | None |  |  | M
| Provide an option to add notes for OFT members and customer​ | Only customer related comments will be shown on Customer portal while both type of comments will be shown in Back-office
11 | Relocation Enhancement- | This feature will allow Ricoh teams to edit contact information up to 3 business days prior to move book date present on the request to contact the right person at collection and delivery site by technicians/installers | All OpCos | Yes | To be started | None |  |  | L
Edit customer contact information up to <3 business days prior to booked date so that data can be edited if something is entered incorrectly instead of cancelling and ask customer to submit fresh request.​
12 | Relocation Enhancement- | This feature will allow Ricoh internal teams to allow enter $0 on submitted requests such that free relocations or governmnent agencies relocations can be proceeded without charging anything to customer for relocating a device | All OpCos | Yes | To be started | None |  |  | S
Allow OFT in back-office to quote with no charges for relocation
13 | Relocation Enhancement- | This feature allow customers to track the Ricoh reference number more efficiently for communication with Ricoh teams in case of any support is needed. Also, in future when logistics APIs are integrated, it will be accomodated and mapped with their reference number as some of the logistics units does not accept large length numbers | All OpCos | Yes | To be started | None |  |  | XS
As an OFT member, I want the MACD reference number to be Less than 16 characters​
14 | Relocation Enhancement- | This feature will allow users to NOT miss the entry of contact information on Delivery Site section. Currently, keeping the checkbox selected, they miss changing the information and leading to cancellation or editing of information needed post submission of request | All OpCos | Yes | To be started | None |  |  | XS
Contact Details not to be preselected in form​
15 | Relocation Enhancement- | This feature will allow customer to raise a request based on time zone and do not allow them to submit on weekends | All OpCos | Yes | On Hold | Video to be shared by Bobi | 15-Jan
Date time needs to be adjusted such that GMT is fulfilled on MACD form​
16 | Relocation Enhancement- | This feature will allow customer to view auto-calculation of quotation while submitting the request. This will reduce the burden of Ricoh internal teams for providing quotation and follow-up with customer for the same. |  | Yes | On Hold | Quote API to be created by Wilkin for RNZ | 2025-01-16 |  | M
Allow request to auto calculate the price based on answers provided by customer user. Currently laserfiche form indicates the price as the customer is logging​
20 | Relocation Enhancement- | This feature will allow Ricoh logicstcs team to plan their deliveries once notified | RPH, RNZ | Yes | To be started | None |  |  | M
Provide an option to send email to logistics team once Booking reference number is added to Relocation request​​
21 | Relocation Enhancement- | This feature will allow customers to request relocation on priority basis and charges will be paid by the customer. | All OpCos | Yes | On Hold | Existing Quote API requires an update to capture priority charges for RNZ and RAP | 2025-01-16 |  | L
| As a customer, I want to be able to request urgent relocations with less than 10 days but more than 4 days notice and pay priority fees, so that my urgent request can still be completed. TBC for timeframes​ | This feature provides Express feature for relocation to customer and allow Ricoh to enhance customer experience meeting customer needs
No dependency for RPH
22 | Relocation Enhancement- | In RAP, they receive ~1200-1400 requests monthly which is difficult to manage and track who is working on what. This feature allow OFT manager to assign requests to its teams and let them work on them dedicatedly. | RAP | Yes | To be started | None |  |  | L
As an OFT member, I want to be able to allocate move requests to team members, so that we know who is responsible for follow up​
25 | Relocation Enhancement- | This feature allow Ricoh internal team to save their changes while providing quote on the submitted requests. This will allow them editing in multiple iterations instead of doing in single iterations. Also, this feature will allow them to view the versions shown to the customer vs shown to the internal Ricoh user for better understanding of the request | All OpCos | Yes | To be started | None |  |  | XL
Provision of saving a draft in BO to OFT user ​
26 | Closed Ticket enhancement | This enhancement will allow user to view last 12 months data for closed ticket especially for the customer who gets onboarded post go-live of the OpCo | All OpCos | Yes | On Hold | Service ticket API to be updated | 2025-01-16 |  | M